## KH Wind Internal
FY 2025-26 ¦ Khavda Wind Projects Monthly Commissioning Plan (MWac) (Phase-02 Carry forward) | [13 empty] | For Internal Purpose | [6 empty] | Date : 08-Dec-25
Sl. | Project | SPV | Category | Total Capacity (MW) | Total WTG Nos. | PSS No. | PSS Charging Date | Till Mar-25 | 2025-04-01 | 2025-05-01 | 2025-06-01 | 2025-07-01 | 2025-08-01 | 2025-09-01 | 2025-10-01 | 2025-11-01 | 2025-12-01 | 2026-01-01 | 2026-02-01 | 2026-03-01 | FY 25-26 Total (Plan) |  | FY 25-26 Commissioned till Nov-25 |  | FY 24-25 Commissioned |  | Total Commissioned till Nov-25
[21 empty] | WTG | MW | WTG | MW | WTG | MW | WTG | MW
1 | Hybrid Port (Wind) | APSEZ | Group | 20.8 | 4 | PSS-3 | Charged | 20.8 | [12 empty] | 0 | 0 | 0 | 0 | 4 | 20.8 | 4 | 20.8 |  | 0
2 | AGEL Merchant (Wind) | ARE41L | Merchant | 260 | 50 | PSS-3 | Charged | 260 | [12 empty] | 0 | 0 | 0 | 0 | 50 | 260 | 50 | 260 |  | 0
3 | AGEL Hybrid Merchant (Wind) | ARE48L AGE25BL | Merchant | 119.6 | 23 | PSS-09 | Charged | 119.6 | [12 empty] | 0 | 0 | 0 | 0 | 23 | 119.6 | 23 | 119.6 |  | 0 | 5229
4 | AGEL Merchant (Wind) | ARE41L | Merchant | 124.8 | 24 | PSS-13 | Charged | 124.8 | [12 empty] | 0 | 0 | 0 | 0 | 24 | 124.8 | 24 | 124.8 |  | 0
5 | AGEL Merchant (Wind) | AGE24L | Merchant | 104 | 20 | PSS-04 | Charged | 52 | 2025-04-01: 52 | 10 | 52 | 10 | 52 | 10 | 52 | 20 | 104 |  | 0 | 4
6 | Hybrid Cement (Wind) | ACL | Group | 156 | 30 | PSS-04 | Charged | 98.8 | 2025-05-01: 26; 2025-06-01: 31.2 | 11 | 57.2 | 11 | 57.2 | 19 | 98.8 | 30 | 156 |  | 0
7 | Hybrid Port (Wind) | APSEZ | Group | 52 | 10 | PSS-04 | Charged | 52 | [12 empty] | 0 | 0 | 0 | 0 | 10 | 52 | 10 | 52 |  | 0
8 | AGEL Merchant (Wind) | AHEJ5L | Merchant | 62.4 | 12 | PSS-04 | Charged |  | 2025-04-01: 52; 2025-06-01: 10.4 | 12 | 62.4 | 12 | 62.4 | 0 |  | 12 | 62.4 |  | 0 | 2.4
9 | AESL PPA (C&I) - Wind - RSWM | ARE41L | Merchant | 52 | 10 | PSS-04 | Charged | 52 | [12 empty] | 0 | 0 | 0 | 0 | 10 | 52 | 10 | 52 |  | 0
10 | AGEL Hybrid Merchant (Wind) | AGE26BL | Merchant | 156 | 30 | PSS-10 | Charged |  | 2025-06-01: 119.6; 2025-07-01: 26; 2026-03-01: 10.4 | 30 | 156 | 28 | 145.6 | 0 |  | 28 | 145.6 |  | 0
11 | AGEL Merchant (Wind) | AHEJ5L | Merchant | 67.6 | 13 | PSS-08 | Charged |  | 2025-09-01: 31.2; 2025-11-01: 31.2; 2026-01-01: 5.2 | 13 | 67.6 | 12 | 62.4 | 0 |  | 12 | 62.4 |  | 0 |  | SPV | PSS | WTGs | MW
12 | AGEL Merchant (Wind) | ARE41L | Merchant | 130 | 25 | PSS-08 | Charged |  | 2025-08-01: 124.8; 2025-11-01: 5.2 | 25 | 130 | 25 | 130 | 0 |  | 25 | 130 |  | 0 |  | AHEJ5L | PSS-08 | 7 | 36.4
13 | Google Hybrid (Wind) | ARE3L | Merchant | 15.6 | 3 | PSS-08 | Charged |  | 2025-07-01: 15.6 | 3 | 15.6 | 3 | 15.6 | 0 |  | 3 | 15.6 |  | 0 |  | ARE41L | PSS-08 | 1 | 5.2
Monthwise FY 24-25 Projects (A) - Total (MW) |  |  |  | 1320.8 |  |  |  | 780 | 104 | 26 | 161.2 | 41.6 | 124.8 | 31.2 | 0 | 36.4 | 0 | 5.2 | 0 | 10.4 | 104 | 540.8 | 101 | 525.2 | 150 | 780 | 251 | 1305.2 |  |  |  | ASEJ6PL | PSS-08 | 10 | 52
Total (No of WTG's) |  |  |  |  | 254 |  |  | 150 | 20 | 5 | 31 | 8 | 24 | 6 | 0 | 7 | 0 | 1 | 0 | 2 | [11 empty] | AHEJ5L (PPA) | PSS-05 | 18 | 93.6
[32 empty] | Total |  | 36 | 187.2
[7 empty] | Category | Till Dec-24 |  |  |  | 2025-07-01 | 2025-08-01 | 2025-09-01 | 2025-10-01 | 2025-11-01 | 2025-12-01 | 2026-01-01 | 2026-02-01 | 2026-03-01
[7 empty] | Merchant | 608.4 |  |  |  | 41.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10.4
[7 empty] | PPA | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | Group | 171.6 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | EPC | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | Total | 780 |  |  |  | 41.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10.4
96
FY 2025-26 ¦ Khavda Wind Projects Monthly Commissioning Plan (MWac) (Phase-03)
Sl. | Project | SPV | Category | Total Capacity (MW) | Total WTG Nos. | PSS No. | PSS Charging Date | Till Mar-25 | 2025-04-01 | 2025-05-01 | 2025-06-01 | 2025-07-01 | 2025-08-01 | 2025-09-01 | 2025-10-01 | 2025-11-01 | 2025-12-01 | 2026-01-01 | 2026-02-01 | 2026-03-01 | FY 25-26 Total (Plan) |  | FY 25-26 Commissioned till Nov-25 |  | FY 24-25 Commissioned |  | Total Commissioned till Nov-25
[21 empty] | WTG | MW | WTG | MW | WTG | MW | WTG | MW
1 | Google Hybrid (Wind) | ARE3L | Merchant | 26 | 5 | PSS-08 | Charged |  | 2025-07-01: 26; 2025-12-01: nnd--2 | 5 | 26 | 5 | 26 | NA | NA | 5 | 26 | 22.8846 | 17.8846
2 | AGEL Hybrid Merchant (Wind) | ASEJ6PL | Merchant | 62.4 | 12 | PSS-08 | Charged |  | 2025-12-01: 20.8; 2026-01-01: 15.6; 2026-02-01: 26 | 12 | 62.4 | 0 | 0 | NA | NA | 0 | 0 | 26.3077 | 14.3077
3 | AGEL Merchant (Wind) | AGE25BL | Merchant | 10.4 | 2 | PSS-09 | Charged |  | 2025-12-01: 5.2; 2026-01-01: 5.2 | 2 | 10.4 | 0 | 0 | NA | NA | 0 | 0 | 4.3846 | 2.3846
4 | SECI H-3 (Wind) | AHEJ5L | PPA | 202.8 | 39 | PSS-05 | Charged |  | 2025-10-01: 78; 2025-11-01: 83.2; 2025-12-01: 20.8; 2026-03-01: 20.8 | 39 | 202.8 | 31 | 161.2 | NA | NA | 31 | 161.2 | 159.4231 | 120.4231
5 | AGEL Merchant (Wind) | AGE25CL | Merchant | 187.2 | 36 | PSS-11 | 2025-08-31 |  | 2025-12-01: 104; 2026-01-01: 78; 2026-02-01: 5.2 | 36 | 187.2 | 0 | 0 | NA | NA | 0 | 0 | 78.9231 | 42.9231
6 | AGEL Merchant (Wind) | AGE26AL | Merchant | 140.4 | 27 | PSS-12 | 2025-08-31 |  | 2026-01-01: 98.8; 2026-02-01: 41.6 | 27 | 140.4 | 0 | 0 | NA | NA | 0 | 0 | 59.1923 | 32.1923
8 | AGEL Merchant (Wind) | AGE25CL | Merchant | 67.6 | 13 | PSS-14 | 2025-11-30 |  | 2026-02-01: 26; 2026-03-01: 41.6 | 13 | 67.6 | 0 | 0 | NA | NA | 0 | 0 | 28.5 | 15.5
9 | AGEL Merchant (Wind) | AGE26AL | Merchant | 312 | 60 | PSS-14 | 2025-11-30 |  | 2026-01-01: 20.8; 2026-02-01: 124.8; 2026-03-01: 166.4 | 60 | 312 | 0 | 0 | NA | NA | 0 | 0 | 131.5385 | 71.5385
Monthwise FY 25-26 Projects (B) - Total (MW) |  |  |  | 1008.8 |  |  |  | 0 | 0 | 0 | 0 | 26 | 0 | 0 | 78 | 83.2 | 150.8 | 218.4 | 223.6 | 228.8 | 194 | 1008.8 | 36 | 187.2 | NA | NA | 36 | 187.2
Monthwise FY 25-26 Projects (B) - Total (WTGs) |  |  |  |  | 194 |  |  | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 15 | 16 | 29 | 42 | 43 | 44
Monthwise FY 24-26 Projects (A+B) - Total (MW) |  |  |  | 2329.6 |  |  |  | 780 | 104 | 26 | 161.2 | 67.6 | 124.8 | 31.2 | 78 | 119.6 | 150.8 | 223.6 | 223.6 | 239.2 | 298 | 1549.6 | 137 | 712.4 | 150 | 780 | 287 | 1492.4
[9 empty] | 2025-04-01: 291.2; 2025-07-01: 223.6; 2025-10-01: 348.4; 2026-01-01: 686.4 | 0
Monthwise FY 24-26 Projects (A+B) - Total (WTGs) |  |  |  |  | 448 |  |  | 150 | 20 | 5 | 31 | 13 | 24 | 6 | 15 | 23 | 29 | 43 | 43 | 46
[7 empty] | 0 |  | 2025-04-01: 56; 2025-07-01: 43; 2025-10-01: 67; 2026-01-01: 132
Note : WTG Commissioning of PSS-11 & 12 is linked with PSS charging.
[7 empty] | PSS Charging Date | Till Mar-25 | 2025-04-01 | 2025-05-01 | 2025-06-01 | 2025-07-01 | 2025-08-01 | 2025-09-01 | 2025-10-01 | 2025-11-01 | 2025-12-01 | 2026-01-01 | 2026-02-01 | 2026-03-01 | FY 25-26 Total (Plan) |  | FY 25-26 Commissioned till Nov-25 |  | FY 24-25 Commissioned |  | Total Commissioned till Nov-25
[21 empty] | WTG | MW | WTG | MW | WTG | MW | WTG | MW
| Overall Status | WTG | MW |  |  | PPA | PPA | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 78 | 83.2 | 20.8 | 0 | 0 | 20.8 | 39 | 202.8 | 31 | 161.2 | 0 | 0 | 31 | 161.2
| Total Plan | 448 | 2329.6 |  |  | Merchant | Merchant | 608.4 | 104 | 0 | 130 | 67.6 | 124.8 | 31.2 | 0 | 36.4 | 130 | 223.6 | 223.6 | 218.4 | 248 | 1289.6 | 95 | 494 | 117 | 608.4 | 212 | 1102.4
| Total Actual | 287 | 1492.4 |  |  | Group | Group | 171.6 | 0 | 26 | 31.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11 | 57.2 | 11 | 57.2 | 33 | 171.6 | 44 | 228.8
[7 empty] | Total | 780 | 104 | 26 | 161.2 | 67.6 | 124.8 | 31.2 | 78 | 119.6 | 150.8 | 223.6 | 223.6 | 239.2 | 298 | 1549.6 | 137 | 712.4 | 150 | 780 | 287 | 1492.4
FY 2024-26 ¦ Khavda Wind Projects Monthly Commissioning Plan (MWac)
[7 empty] | Category | Till Dec-24 | 2025-04-01: 2025-04-01; 2025-05-01: 2025-05-01; 2026-01-01: 2026-01-01; 2026-02-01: 2026-02-01; 2026-03-01: 2026-03-01
[7 empty] | Merchant | 1216.8 | 2025-04-01: 104; 2025-05-01: 0; 2026-01-01: 223.6; 2026-02-01: 223.6; 2026-03-01: 228.8
[7 empty] | PPA | 0 | 2025-04-01: 0; 2025-05-01: 0; 2026-01-01: 0; 2026-02-01: 0; 2026-03-01: 20.8
[7 empty] | Group | 343.2 | 2025-04-01: 0; 2025-05-01: 26; 2026-01-01: 0; 2026-02-01: 0; 2026-03-01: 0
[7 empty] | EPC | #REF! | 2025-04-01: #REF!; 2025-05-01: #REF!; 2026-01-01: #REF!; 2026-02-01: #REF!; 2026-03-01: #REF!
[7 empty] | Total | #REF! | 2025-04-01: #REF!; 2025-05-01: #REF!; 2026-01-01: #REF!; 2026-02-01: #REF!; 2026-03-01: #REF!
[8 empty] | #REF! | 2025-04-01: #REF!; 2025-05-01: #REF!; 2026-01-01: #REF!; 2026-02-01: #REF!; 2026-03-01: #REF!
[9 empty] | #REF! | [9 empty] | #REF!
[8 empty] | #REF! | 2025-04-01: #REF!; 2025-05-01: #REF!; 2026-01-01: #REF!; 2026-02-01: #REF!; 2026-03-01: #REF!
[9 empty] | #REF! | [9 empty] | #REF!
[9 empty] | 0 | 0 | [7 empty] | 42 | 43 | 44
[9 empty] | 104 | 26 | [7 empty] | 223.6 | 223.6 | 239.2
Formulas:
PSS Charging Date = '[1]FY 24-26 Khavda Solar '!M31