## Page_1_Table_1
| AGEL FY 25-26 Commissioning Status Update | [7 empty] | For Chairman Budget Purpose @6.5GW +535 MW carryover | [10 empty] | 31-Oct-25
[12 empty] | Monthwise Distribution | [9 empty] | Quarterly Distribution
[19 empty] | Total | Cumm till
[6 empty] | Plan / Actual | Apr-25 | May-25 | Jun-25 | Jul-25 | Aug-25 | Sep-25 | Oct-25 | Nov-25 | Dec-25 | Jan-26 | Feb-26 | Mar-26 |  |  | Q1 | Q2 | Q3 | Q4
[19 empty] | Capacity | 31-Oct-25
[6 empty] | Plan | 1115 | 532 | 1546 | 644 | 26 | 459 | 419 | 655 | 1039 | 562 |  | 76 | 7073 | 4741 | 3193 | 1129 | 2113 | 638
[6 empty] | PPA | 583 |  | 475 | 623 | 26 | 459 | 419 | 351 | 909 | 300 |  |  | 4144 | 2584 | 1058 | 1108 | 1679 | 300
[6 empty] | Merchant | 506 | 501 | 646 | 21 |  |  |  | 304 | 130 | 262 |  | 76 | 2446 | 1674 | 1653 | 21 | 434 | 338
[6 empty] | Group | 26 | 31 | 425 | [9 empty] | 482 | 482 | 482
[6 empty] | Rephase | 474 | 314 | 849 | 576 | 653 | 353 | 367 | 459 | 783 | 971 | 880 | 396 | 7073 | 3584 | 1636 | 1582 | 1608 | 2247
| AGEL Overall FY 2025-26 |  |  |  |  | PPA | 320 | 163 | 463 | 188 | 150 | 200 | 100 | 254 | 783 | 717 | 550 | 258 | 4144 | 1583 | 945 | 538 | 1137 | 1525
(1+2) | [5 empty] | Merchant | 154 | 125 | 355 | 238 | 278 | 153 | 217 | 205 |  | 254 | 330 | 138 | 2446 | 1520 | 634 | 669 | 421 | 722
[6 empty] | Group |  | 26 | 31 | 150 | 225 |  | 50 | [5 empty] | 482 | 482 | 57 | 375 | 50
[6 empty] | Actual / Fcst | 474 | 314 | 849 | 128 | 537 | 531 | 203 | 720 | 568 | 1169 | 597 | 985 | 7073 | 3035 | 1636 | 1196 | 1490 | 2750
[6 empty] | PPA | 320 | 163 | 463 |  | 138 | 175 | 203 | 433 | 242 | 925 | 400 | 684 | 4144 | 1461 | 945 | 313 | 878 | 2009
[6 empty] | Merchant | 154 | 125 | 355 | 128 | 250 | 306 |  | 136 | 251 | 244 | 197 | 301 | 2446 | 1318 | 634 | 684 | 387 | 741
[6 empty] | Group |  | 26 | 31 |  | 150 | 50 |  | 150 | 75 |  |  |  | 482 | 257 | 57 | 200 | 225
[19 empty] | Total | Cumm till
[6 empty] | Plan / Actual | Apr-25 | May-25 | Jun-25 | Jul-25 | Aug-25 | Sep-25 | Oct-25 | Nov-25 | Dec-25 | Jan-26 | Feb-26 | Mar-26 |  |  | Q1 | Q2 | Q3 | Q4
[19 empty] | Capacity | 31-Oct-25
[6 empty] | Plan | 933 | 350 | 1302 | 550 |  | 433 | 367 | 525 | 909 | 500 |  |  | 5869 | 3935 | 2585 | 983 | 1801 | 500
[6 empty] | PPA | 583 |  | 475 | 550 |  | 433 | 367 | 325 | 909 | 300 |  |  | 3942 | 2408 | 1058 | 983 | 1601 | 300
[6 empty] | Merchant | 350 | 350 | 402 |  |  |  |  | 200 |  | 200 |  |  | 1502 | 1102 | 1102 |  | 200 | 200
[6 empty] | Group |  |  | 425 | [9 empty] | 425 | 425 | 425
[6 empty] | Rephase | 370 | 288 | 688 | 498 | 575 | 275 | 263 | 355 | 684 | 867 | 750 | 258 | 5869 | 2955 | 1345 | 1348 | 1301 | 1875
| 1. AGEL Overall Solar FY 2025-26 |  |  |  |  | PPA | 320 | 163 | 463 | 188 | 150 | 200 | 100 | 150 | 684 | 717 | 550 | 258 | 3942 | 1583 | 945 | 538 | 934 | 1525
(A + B + C) | [5 empty] | Merchant | 50 | 125 | 225 | 160 | 200 | 75 | 113 | 205 |  | 150 | 200 |  | 1502 | 948 | 400 | 435 | 317 | 350
[6 empty] | Group |  |  |  | 150 | 225 |  | 50 | [5 empty] | 425 | 425 |  | 375 | 50
[6 empty] | Actual / Fcst | 370 | 288 | 688 | 60 | 413 | 500 | 125 | 600 | 438 | 1075 | 467 | 847 | 5869 | 2443 | 1345 | 973 | 1163 | 2389
[6 empty] | PPA | 320 | 163 | 463 |  | 138 | 175 | 125 | 350 | 200 | 925 | 400 | 684 | 3942 | 1383 | 945 | 313 | 675 | 2009
[6 empty] | Merchant | 50 | 125 | 225 | 60 | 125 | 275 |  | 100 | 163 | 150 | 67 | 163 | 1502 | 860 | 400 | 460 | 263 | 380
[6 empty] | Group |  |  |  |  | 150 | 50 |  | 150 | 75 |  |  |  | 425 | 200 |  | 200 | 225
Plot /
[19 empty] | Total | Cumm till
S. No. | Project Name | SPV | Type | Location / | Capacity | Plan Actual | Apr-25 | May-25 | Jun-25 | Jul-25 | Aug-25 | Sep-25 | Oct-25 | Nov-25 | Dec-25 | Jan-26 | Feb-26 | Mar-26 |  |  | Q1 | Q2 | Q3 | Q4
[19 empty] | Capacity | 31-Oct-25
PSS
A. Khavda Solar Projects
[6 empty] | Plan | 150 | 100 | [10 empty] | 250 | 250 | 250
1 | AGEL Merchant | ARE56L | Merchant | S-08 | 250 | Rephase |  | 75 | 50 | 50 | 75 | [7 empty] | 250 | 250 | 125 | 125
[6 empty] | Actual / Fcst |  | 75 | 50 |  | 125 | [7 empty] | 250 | 250 | 125 | 125
[6 empty] | Plan | 50 | [11 empty] | 50 | 50 | 50
2 | AGEL Merchant | ARE56L | Merchant | A-02 | 50 | Rephase |  | 50 | [10 empty] | 50 | 50 | 50
[6 empty] | Actual / Fcst |  | 50 | [10 empty] | 50 | 50 | 50
[6 empty] | Plan | 188 | [11 empty] | 188 | 188 | 188
3 | MLP AP New | ARE57L | PPA | A-11 | 187.5 | Rephase | 75 | 113 | [10 empty] | 188 | 188 | 188
[6 empty] | Actual / Fcst | 75 | 113 | [10 empty] | 188 | 188 | 188
[6 empty] | Plan |  |  | 100 | 250 | [8 empty] | 350 | 350 | 100 | 250
4 | MLP AP New | ARE57L | PPA | A-12 | 350 | Rephase |  | 50 | 175 |  | 75 | 50 | [6 empty] | 350 | 350 | 225 | 125
[6 empty] | Actual / Fcst |  | 50 | 175 |  |  |  |  | 125 |  |  |  |  | 350 | 225 | 225 |  | 125
[6 empty] | Plan | 295 |  | 275 | [9 empty] | 570 | 570 | 570
5 | SECI H-3 | AHEJ5L | PPA | A-13 | 570 | Rephase | 145 |  | 150 | 75 |  | 50 | 50 | 100 |  |  |  |  | 570 | 470 | 295 | 125 | 150
[6 empty] | Actual / Fcst | 145 |  | 150 |  | 50 | 75 | 75 | 75 |  |  |  |  | 570 | 495 | 295 | 125 | 150
[6 empty] | Plan | 150 | 100 | [10 empty] | 250 | 250 | 250
6 | AGEL Merchant | ARE45L | Merchant | A-14 | 250 | Rephase | 50 |  | 125 |  | 75 | [7 empty] | 250 | 250 | 175 | 75
[6 empty] | Actual / Fcst | 50 |  | 125 |  |  | 75 | [6 empty] | 250 | 250 | 175 | 75
[6 empty] | Plan | 100 |  | 100 | 300 | [8 empty] | 500 | 500 | 200 | 300
7 | MLP T3 AP | ARE56L | PPA | S-06 | 500 | Rephase | 100 |  | 138 | 113 |  | 50 | 50 | 50 |  |  |  |  | 500 | 450 | 238 | 163 | 100
[6 empty] | Actual / Fcst | 100 |  | 138 |  | 88 | 100 |  | 75 |  |  |  |  | 500 | 425 | 238 | 188 | 75
[6 empty] | Plan |  |  | 25 | [9 empty] | 25 | 25 | 25
8 | Google Hybrid | ARE3L | Merchant | A-6 | 25 | Rephase |  |  |  | 25 | [8 empty] | 25 | 25 |  | 25
[6 empty] | Actual / Fcst |  |  |  | 25 | [8 empty] | 25 | 25 |  | 25
[6 empty] | Plan |  |  | 35 | [9 empty] | 35 | 35 | 35
9 | AGEL Merchant | ASEJ6PL | Merchant | A-6 | 35 | Rephase |  |  |  | 35 | [8 empty] | 35 | 35 |  | 35
[6 empty] | Actual / Fcst |  |  |  | 35 | [8 empty] | 35 | 35 |  | 35
[6 empty] | Plan | [9 empty] | 100 |  |  | 100 |  |  |  |  | 100
10 | AGEL Hybrid Merchant | AGE25BL | Merchant | S-8 | 100 | Rephase |  |  |  |  | 50 |  |  | 50 |  |  |  |  | 100 | 50 |  | 50 | 50
[6 empty] | Actual / Fcst | [5 empty] | 100 | [6 empty] | 100 | 100 |  | 100
[6 empty] | Plan | [7 empty] | 50 |  | 100 |  |  | 150 |  |  |  | 50 | 100
11 | AGEL Merchant | AHEJ5L | Merchant | A-15a | 150 | Rephase | [6 empty] | 50 | 50 |  | 50 |  |  | 150 | 50 |  |  | 100 | 50
[6 empty] | Actual / Fcst | [5 empty] | 50 |  |  | 100 |  |  |  | 150 | 50 |  | 50 | 100
[6 empty] | Plan |  | 100 | 192 | [9 empty] | 292 | 292 | 292
12 | AGEL Hybrid Merchant | AGE26BL | Merchant | S-5 | 292 | Rephase |  |  |  | 50 |  | 75 | 63 | 105 |  |  |  |  | 292 | 188 |  | 125 | 167
[6 empty] | Actual / Fcst | [5 empty] | 50 |  | 100 |  | 75 | 67 |  | 292 | 50 |  | 50 | 100 | 142
[6 empty] | Plan |  | 50 | 100 | [9 empty] | 150 | 150 | 150
13 | AGEL Merchant | AGE24L | Merchant | S-5 | 150 | Rephase | [9 empty] | 50 | 100 |  | 150 |  |  |  |  | 150
[6 empty] | Actual / Fcst | [8 empty] | 63 |  |  | 88 | 150 |  |  |  | 63 | 88
[6 empty] | Plan | [7 empty] | 150 |  |  |  |  | 150 |  |  |  | 150
14 | AGEL Merchant | AGE24L | Merchant | A-14 | 150 | Rephase | [9 empty] | 50 | 100 |  | 150 |  |  |  |  | 150
[6 empty] | Actual / Fcst | [9 empty] | 75 |  | 75 | 150 |  |  |  |  | 150
[6 empty] | Plan |  |  | 125 | [9 empty] | 125 | 125 | 125
15 | Cement - Hybrid | ACL | Group | A-1 | 125 | Rephase |  |  |  |  | 75 |  | 50 | [5 empty] | 125 | 125 |  | 75 | 50
[6 empty] | Actual / Fcst | [5 empty] | 50 |  |  | 75 |  |  |  | 125 | 50 |  | 50 | 75
[6 empty] | Plan | [7 empty] | 75 |  |  |  |  | 75 |  |  |  | 75
16 | MLP T3 AP | AGE25CL | PPA | A-6 | 75 | Rephase |  |  |  |  | 75 | [7 empty] | 75 | 75 |  | 75
[6 empty] | Actual / Fcst | [7 empty] | 75 |  |  |  |  | 75 |  |  |  | 75
[6 empty] | Plan | [5 empty] | 50 | [6 empty] | 50 | 50 |  | 50
17 | MLP T1 J&K | AGE26AL | PPA | A-16 | 50 | Rephase | [8 empty] | 50 |  |  |  | 50 |  |  |  | 50
[6 empty] | Actual / Fcst | [8 empty] | 50 |  |  |  | 50 |  |  |  | 50
[6 empty] | Plan | [6 empty] | 200 | [5 empty] | 200 | 200 |  |  | 200
18 | MLP T1 CG | AGE26AL | PPA | A-16 | 200 | Rephase | [8 empty] | 50 | 100 | 50 |  | 200 |  |  |  | 50 | 150
[6 empty] | Actual / Fcst | [8 empty] | 50 | 100 | 50 |  | 200 |  |  |  | 50 | 150
[6 empty] | Plan | [6 empty] | 167 | [5 empty] | 167 | 167 |  |  | 167
19 | MLP T1 TN | AGE26AL | PPA | A-16 | 167 | Rephase | [8 empty] | 50 | 117 |  |  | 167 |  |  |  | 50 | 117
[6 empty] | Actual / Fcst | [9 empty] | 100 | 67 |  | 167 |  |  |  |  | 167
[6 empty] | Plan | [5 empty] | 333 | [6 empty] | 333 | 333 |  | 333
20 | MLP T1 OR | AGE26AL | PPA | A-16 | 333 | Rephase | [9 empty] | 100 | 100 | 133 | 333 |  |  |  |  | 333
[6 empty] | Actual / Fcst | [9 empty] | 200 | 133 |  | 333 |  |  |  |  | 333
[6 empty] | Plan | [5 empty] | 50 | [6 empty] | 50 | 50 |  | 50
21 | MLP T1 TR | AGE26AL | PPA | A10a | 50 | Rephase | [5 empty] | 50 | [6 empty] | 50 | 50 |  | 50
[6 empty] | Actual / Fcst | [6 empty] | 50 | [5 empty] | 50 | 50 |  |  | 50
[6 empty] | Plan | [8 empty] | 425 |  |  |  | 425 |  |  |  | 425
22 | MLP T3 AP | AGE25CL | PPA | A-6 | 425 | Rephase | [9 empty] | 150 | 150 | 125 | 425 |  |  |  |  | 425
[6 empty] | Actual / Fcst | [8 empty] | 100 | 325 |  |  | 425 |  |  |  | 100 | 325
[6 empty] | Plan | 933 | 350 | 952 | 550 |  | 433 | 367 | 275 | 425 | 200 |  |  | 4485 | 3585 | 2235 | 983 | 1067 | 200
[6 empty] | PPA | 583 |  | 475 | 550 |  | 433 | 367 | 75 | 425 |  |  |  | 2908 | 2408 | 1058 | 983 | 867
[6 empty] | Merchant | 350 | 350 | 352 |  |  |  |  | 200 |  | 200 |  |  | 1452 | 1052 | 1052 |  | 200 | 200
[6 empty] | Group |  |  | 125 | [9 empty] | 125 | 125 | 125
[6 empty] | Rephase | 370 | 288 | 638 | 348 | 425 | 275 | 263 | 355 | 150 | 617 | 500 | 258 | 4485 | 2605 | 1295 | 1048 | 767 | 1375
[6 empty] | PPA | 320 | 163 | 463 | 188 | 150 | 200 | 100 | 150 | 150 | 467 | 300 | 258 | 2908 | 1583 | 945 | 538 | 400 | 1025
| A. Subtotal (Khavda Solar Projects) |  |  |  | 4485
[6 empty] | Merchant | 50 | 125 | 175 | 160 | 200 | 75 | 113 | 205 |  | 150 | 200 |  | 1452 | 898 | 350 | 435 | 317 | 350
[6 empty] | Group |  |  |  |  | 75 |  | 50 | [5 empty] | 125 | 125 |  | 75 | 50
[6 empty] | Actual / Fcst | 370 | 288 | 638 | 60 | 263 | 500 | 125 | 450 | 438 | 875 | 317 | 163 | 4485 | 2243 | 1295 | 823 | 1013 | 1355
[6 empty] | PPA | 320 | 163 | 463 |  | 138 | 175 | 125 | 350 | 200 | 725 | 250 |  | 2908 | 1383 | 945 | 313 | 675 | 975
[6 empty] | Merchant | 50 | 125 | 175 | 60 | 125 | 275 |  | 100 | 163 | 150 | 67 | 163 | 1452 | 810 | 350 | 460 | 263 | 380
[6 empty] | Group | [5 empty] | 50 |  |  | 75 |  |  |  | 125 | 50 |  | 50 | 75

## Page_2_Table_2
[6 empty] | Plan | 12.5 | 12.5 | 12.5
26 | MCIPL | MCIPL | Group | A-15a | 12.5 | Rephase | 12.5 | 12.5 | 12.5
[6 empty] | Actual / Fcst | 12.5 | 12.5 | 12.5
[6 empty] | Plan | 25 | 25 | 25
27 | AGEL Merchant | ASEJo6PL | Merchant | A-15a | 25 | Rephase | 25 | 25 | 25
[6 empty] | Actual / Fcst | 25 | 25 | 25
[6 empty] | Plan | 50 | 50 | 50
PPA
[6 empty] | Merchant | 25 | 25 | 25
[6 empty] | Group | 25 | 25 | 25
[6 empty] | Rephase | 50 | 50 | 50
D1. Khavda Solar | [5 empty] | PPA
50
(Copper + Merchant - 50 MW) | [5 empty] | Merchant | 25 | 25 | 25
[6 empty] | Group | 25 | 25 | 25
[6 empty] | Actual / Fcst | 50 | 50 | 50
PPA
[6 empty] | Merchant | 25 | 25 | 25
[6 empty] | Group | 25 | 25 | 25

## Page_2_Table_3
[5 empty] | Group |  |  | 25 | 25 |  | 25
D2. Khavda Solar (Additional for Internal - 650 MW)
[5 empty] | Plan |  | 150 | 200 | 350 |  | 350
23AGEL Hybrid Merchant | AHEJ5L | Merchant | S-4 | 300 | Rephase | 100 | 100 | 100 | 300 | 100 | 200
Actual / Fcst
[5 empty] | Plan | 100 | 100 | 100 | 300 | 100 | 200
24MLP AP New | ARE57L | PPA | A-12 | 350 | Rephase | 150 | 200 |  | 350 | 150 | 200
[5 empty] | Actual / Fcst |  | 100 | 20050 | 350 |  | 350
[5 empty] | Plan | 100 | 250 | 300 | 650 | 100 | 550
[5 empty] | PPA | 100 | 100 | 100 | 300 | 100 | 200
[5 empty] | Merchant |  | 150 | 200 | 350 |  | 350
Group
[5 empty] | Rephase | 250 | 300 | 100 | 650 | 250 | 400
D2. Khavda Solar |  |  |  |  | PPA | 150 | 200 |  | 350 | 150 | 200
650
(Additional from Internal - 650 MW) |  |  |  |  | Merchant | 100 | 100 | 100 | 300 | 100 | 200
Group
[5 empty] | Actual / Fcst |  | 100 | 20050 | 350 |  | 350
[5 empty] | PPA |  | 100 | 20050 | 350 |  | 350
Merchant

## Page_2_Table_4
PSS
B. Rajasthan Solar Projects
[6 empty] | Plan | 300 |  |  |  | 300 | 300 | 300
1 | Cement RJ | ACL | Group | Essel park | 300 | Rephase | 150 | 150 |  |  | 300 | 300 | 300
[6 empty] | Actual / Fcst |  | 150 | 150 |  | 300 | 150 | 150 | 150
[6 empty] | Plan | 50 |  |  |  | 50 | 50 | 50
2 | Merchant | ASEJ6PL | Merchant | Bap | 50 | Rephase | 50 |  |  |  | 50 | 50 | 50
[6 empty] | Actual / Fcst | 50 |  |  |  | 50 | 50 | 50
[6 empty] | Plan |  |  | 250284 |  | 534 |  |  | 534
3 | MLP AP New | AGE26BL | PPA | Bandha | 534 | Rephase |  |  | 534 |  | 534 |  |  | 534
[6 empty] | Actual / Fcst |  |  |  | 284 | 284 |  |  | 284
[6 empty] | Plan |  |  | 200300 |  | 500 |  |  | 200300
4 | MLP T1 | AGE25BL | PPA | Bandha | 500 | Rephase |  |  | 250250 |  | 500 |  |  | 500
[6 empty] | Actual / Fcst |  |  |  | 250 | 250 |  |  | 250
[6 empty] | Plan | 350 |  | 250484300 |  | 1384 | 350 | 350 | 734300
[6 empty] | PPA |  |  | 250484300 |  | 1034 |  |  | 734300
[6 empty] | Merchant | 50 |  |  |  | 50 | 50 | 50
[6 empty] | Group | 300 |  |  |  | 300 | 300 | 300
[6 empty] | Rephase | 50150 | 150 | 534250250 |  | 1384 | 350 | 50300 | 534500
[6 empty] | PPA |  |  | 534250250 |  | 1034 |  |  | 534500
| B. Rajasthan Solar Projects |  |  |  | 1384
[6 empty] | Merchant | 50 |  |  |  | 50 | 50 | 50
[6 empty] | Group | 150 | 150 |  |  | 300 | 300 | 300
[6 empty] | Actual / Fcst | 50 | 150 | 150 | 534 | 884 | 200 | 50150 | 150534
[6 empty] | PPA |  |  |  | 534 | 534 |  |  | 534
[6 empty] | Merchant | 50 |  |  |  | 50 | 50 | 50
[6 empty] | Group |  | 150 | 150 |  | 300 | 150 | 150 | 150
C. Rajasthan Solar Projects (Additional to Chairman Plan - 500 MW)
Plan
3 | NHPC BOO | ASEB1PL | PPA | Baiya | 600 | Rephase
[6 empty] | Actual / Fcst |  |  | 200150 | 150 | 500 |  |  | 500
Plan
PPA
Merchant
Group
Rephase
| C. Rajasthan Solar Projects |  |  |  |  | PPA
600
| (Additional to Chairman Plan - 500 MW) |  |  |  |  | Merchant
Group
[6 empty] | Actual / Fcst |  |  | 200150 | 150 | 500 |  |  | 500
[6 empty] | PPA |  |  | 200150 | 150 | 500 |  |  | 500
Merchant
Group
D1. Khavda Solar (Copper + Merchant - 50 MW)
[6 empty] | Plan |  |  | 12.5 |  | 12.5 |  |  | 12.5
25 | KCTL | KCTL | Group | A-15a | 12.5 | Rephase |  |  | 12.5 |  | 12.5 |  |  | 12.5
[6 empty] | Actual / Fcst |  |  | 12.5 |  | 12.5 |  |  | 12.5
[6 empty] | Plan |  |  | 12.5 |  | 12.5 |  |  | 12.5
26 | MCIPL | MCIPL | Group | A-15a | 12.5 | Rephase |  |  | 12.5 |  | 12.5 |  |  | 12.5
[6 empty] | Actual / Fcst |  |  | 12.5 |  | 12.5 |  |  | 12.5
[6 empty] | Plan |  |  | 25 |  | 25 |  |  | 25
27 | AGEL Merchant | ASEJo6PL | Merchant | A-15a | 25 | Rephase |  |  | 25 |  | 25 |  |  | 25
[6 empty] | Actual / Fcst |  |  | 25 |  | 25 |  |  | 25
[6 empty] | Plan |  |  | 50 |  | 50 |  |  | 50
PPA
[6 empty] | Merchant |  |  | 25 |  | 25 |  |  | 25
[6 empty] | Group |  |  | 25 |  | 25 |  |  | 25
[6 empty] | Rephase |  |  | 50 |  | 50 |  |  | 50
D1. Khavda Solar | [5 empty] | PPA
50
| (Copper + Merchant - 50 MW) |  |  |  |  | Merchant |  |  | 25 |  | 25 |  |  | 25
[6 empty] | Group |  |  | 25 |  | 25 |  |  | 25
[6 empty] | Actual / Fcst |  |  | 50 |  | 50 |  |  | 50
PPA
[6 empty] | Merchant |  |  | 25 |  | 25 |  |  | 25
[6 empty] | Group |  |  | 25 |  | 25 |  |  | 25
D2. Khavda Solar (Additional for Internal - 650 MW)
[6 empty] | Plan |  |  | 150200 |  | 350 |  |  | 350
23 | AGEL Hybrid Merchant | AHEJ5L | Merchant | S-4 | 300 | Rephase |  |  | 100100100 |  | 300 |  |  | 100200
Actual / Fcst
[6 empty] | Plan |  |  | 100100100 |  | 300 |  |  | 100200
24 | MLP AP New | ARE57L | PPA | A-12 | 350 | Rephase |  |  | 150200 |  | 350 |  |  | 150200
[6 empty] | Actual / Fcst |  |  | 100200 | 50 | 350 |  |  | 350
[6 empty] | Plan |  |  | 100250300 |  | 650 |  |  | 100550
[6 empty] | PPA |  |  | 100100100 |  | 300 |  |  | 100200
[6 empty] | Merchant |  |  | 150200 |  | 350 |  |  | 350
Group
[6 empty] | Rephase |  |  | 250300100 |  | 650 |  |  | 250400
D2. Khavda Solar | [5 empty] | PPA |  |  | 150200 |  | 350 |  |  | 150200
650
| (Additional from Internal - 650 MW) |  |  |  |  | Merchant |  |  | 100100100 |  | 300 |  |  | 100200
Group
[6 empty] | Actual / Fcst |  |  | 100200 | 50 | 350 |  |  | 350
[6 empty] | PPA |  |  | 100200 | 50 | 350 |  |  | 350
Merchant
Group

## Page_3_Table_5
Plot /
[17 empty] | Total | Cumm till
S. No.Project Name SPV | Type | Location / | Capacity | Plan Actual | Apr-25 | May-25 | Jun-25 | Jul-25 | Aug-25 | Sep-25 | Oct-25 | Nov-25 | Dec-25 | Jan-26 | Feb-26 | Mar-26 |  |  | Q1 | Q2 | Q3 | Q4
[17 empty] | Capacity | 31-Oct-25
PSS
|  |  |  | Plan | 182 | 182 | 244 | 94 | 26 | 26 | 52 | 130 | 130 | 62 |  | 76 | 1204 | 806 | 608 | 146 | 312 | 138
|  |  |  | PPA |  |  |  | 73 | 26 | 26 | 52 | 26 |  |  |  |  | 203 | 177 |  | 125 | 78
|  |  |  | Merchant | 156 | 151 | 244 | 21 |  |  |  | 104 | 130 | 62 |  | 76 | 944 | 572 | 551 | 21 | 234 | 138
|  |  |  | Group | 26 | 31 | [10 empty] | 57 | 57 | 57
|  |  |  | Rephase | 104 | 26 | 161 | 78 | 78 | 78 | 104 | 104 | 99 | 104 | 130 | 138 | 1204 | 629 | 291 | 234 | 307 | 372
2. AGEL Overall Wind FY 2025-26 |  |  |  | PPA | [7 empty] | 104 | 99 |  |  |  | 203 |  |  |  | 203
(A + C) |  |  |  | Merchant | 104 |  | 130 | 78 | 78 | 78 | 104 |  |  | 104 | 130 | 138 | 944 | 572 | 234 | 234 | 104 | 372
|  |  |  | Group |  | 26 | 31 | [9 empty] | 57 | 57 | 57
|  |  |  | Actual / Fcst | 104 | 26 | 161 | 68 | 125 | 31 | 78 | 120 | 130 | 94 | 130 | 138 | 1204 | 593 | 291 | 224 | 328 | 362
|  |  |  | PPA | [6 empty] | 78 | 83 | 42 |  |  |  | 203 | 78 |  |  | 203
|  |  |  | Merchant | 104 |  | 130 | 68 | 125 | 31 |  | 36 | 88 | 94 | 130 | 138 | 944 | 458 | 234 | 224 | 125 | 362
|  |  |  | Group |  | 26 | 31 | [9 empty] | 57 | 57 | 57
A. Khavda Wind Projects
|  |  |  | Plan | 52 | [11 empty] | 52 | 52 | 52
1AGEL MerchantAGE24L | Merchant | PSS-04 | 52 | Rephase | 52 | [11 empty] | 52 | 52 | 52
|  |  |  | Actual / Fcst | 52 | [11 empty] | 52 | 52 | 52
|  |  |  | Plan | 26 | 31 | [10 empty] | 57 | 57 | 57
2Hybrid CementACL | Group | PSS-04 | 57.2 | Rephase |  | 26 | 31 | [9 empty] | 57 | 57 | 57
|  |  |  | Actual / Fcst |  | 26 | 31 | [9 empty] | 57 | 57 | 57
|  |  |  | Plan | 52 | 10 | [10 empty] | 62 | 62 | 62
3AGEL MerchantAHEJ5L | Merchant | PSS-04 | 62.4 | Rephase | 52 |  | 10 | [9 empty] | 62 | 62 | 62
|  |  |  | Actual / Fcst | 52 |  | 10 | [9 empty] | 62 | 62 | 62
|  |  |  | Plan | 52 | 104 | [10 empty] | 156 | 156 | 156
4AGEL Hybrid MerchantAGE26BL | Merchant | PSS-10 | 156 | Rephase |  |  | 120 | 26 | 10 | [7 empty] | 156 | 156 | 120 | 36
|  |  |  | Actual / Fcst |  |  | 120 | 26 | [5 empty] | 10 |  |  | 156 | 146 | 120 | 26 |  | 10
|  |  |  | Plan |  |  | 68 | [9 empty] | 68 | 68 | 68
5AGEL MerchantAHEJ5L | Merchant | PSS-08 | 67.6 | Rephase | [5 empty] | 52 | 16 | [5 empty] | 68 | 68 |  | 52 | 16
|  |  |  | Actual / Fcst | [5 empty] | 31 |  | 31 | 5 |  |  |  | 68 | 31 |  | 31 | 36
|  |  |  | Plan |  | 36 | 94 | [9 empty] | 130 | 130 | 130
6AGEL MerchantARE41L | Merchant | PSS-08 | 130 | Rephase |  |  |  | 52 | 26 | 26 | 26 | [5 empty] | 130 | 130 |  | 104 | 26
|  |  |  | Actual / Fcst |  |  |  |  | 125 |  |  | 5 |  |  |  |  | 130 | 125 |  | 125 | 5
|  |  |  | Plan |  |  | 16 | [9 empty] | 16 | 16 | 16
7Google HybridARE3L | Merchant | PSS-08 | 15.6 | Rephase |  |  |  |  | 16 | [7 empty] | 16 | 16 |  | 16
|  |  |  | Actual / Fcst |  |  |  | 16 | [8 empty] | 16 | 16 |  | 16
|  |  |  | Plan |  |  | 26 | [9 empty] | 26 | 26 | 26
8Google HybridARE3L | Merchant | PSS-08 | 26 | Rephase |  |  |  |  | 26 | [7 empty] | 26 | 26 |  | 26
|  |  |  | Actual / Fcst |  |  |  | 26 | [8 empty] | 26 | 26 |  | 26
|  |  |  | Plan |  |  | 42 | 21 | [8 empty] | 62 | 62 | 42 | 21
9AGEL Hybrid MerchantASEJ6PL | Merchant | PSS-08 | 62.4 | Rephase | [6 empty] | 62 | [5 empty] | 62 | 62 |  |  | 62
|  |  |  | Actual / Fcst | [8 empty] | 31 | 31 |  |  | 62 |  |  |  | 31 | 31
|  |  |  | Plan |  |  |  | 73 | 26 | 26 | 52 | 26 |  |  |  |  | 203 | 177 |  | 125 | 78
10SECI H-3AHEJ5L | PPA | PSS-05 | 202.8 | Rephase | [7 empty] | 104 | 99 |  |  |  | 203 |  |  |  | 203
|  |  |  | Actual / Fcst | [6 empty] | 78 | 83 | 42 |  |  |  | 203 | 78 |  |  | 203
|  |  |  | Plan | [7 empty] | 104 | 52 |  |  |  | 156 |  |  |  | 156
11aAGEL MerchantAGE25CL | Merchant | PSS-11 | 156 | Rephase | [9 empty] | 104 | 52 |  | 156 |  |  |  |  | 156
|  |  |  | Actual / Fcst | [8 empty] | 52 | 52 | 52 |  | 156 |  |  |  | 52 | 104
|  |  |  | Plan | [8 empty] | 78 | 62 |  |  | 140 |  |  |  | 78 | 62
12aAGEL MerchantAGE26AL | Merchant | PSS-12 | 140.4 | Rephase | [10 empty] | 78 | 62 | 140 |  |  |  |  | 140
|  |  |  | Actual / Fcst | [10 empty] | 78 | 62 | 140 |  |  |  |  | 140
|  |  |  | Plan | 182 | 182 | 244 | 94 | 26 | 26 | 52 | 130 | 130 | 62 |  |  | 1128 | 806 | 608 | 146 | 312 | 62
|  |  |  | PPA |  |  |  | 73 | 26 | 26 | 52 | 26 |  |  |  |  | 203 | 177 |  | 125 | 78
|  |  |  | Merchant | 156 | 151 | 244 | 21 |  |  |  | 104 | 130 | 62 |  |  | 868 | 572 | 551 | 21 | 234 | 62
|  |  |  | Group | 26 | 31 | [10 empty] | 57 | 57 | 57
|  |  |  | Rephase | 104 | 26 | 161 | 78 | 78 | 78 | 104 | 104 | 99 | 104 | 130 | 62 | 1128 | 629 | 291 | 234 | 307 | 296
|  |  |  | PPA | [7 empty] | 104 | 99 |  |  |  | 203 |  |  |  | 203
A. Subtotal (Khavda Wind Projects) |  |  | 1128
|  |  |  | Merchant | 104 |  | 130 | 78 | 78 | 78 | 104 |  |  | 104 | 130 | 62 | 868 | 572 | 234 | 234 | 104 | 296
|  |  |  | Group |  | 26 | 31 | [9 empty] | 57 | 57 | 57
|  |  |  | Actual / Fcst | 104 | 26 | 161 | 68 | 125 | 31 | 78 | 120 | 130 | 94 | 130 | 62 | 1128 | 593 | 291 | 224 | 328 | 286
|  |  |  | PPA | [6 empty] | 78 | 83 | 42 |  |  |  | 203 | 78 |  |  | 203
|  |  |  | Merchant | 104 |  | 130 | 68 | 125 | 31 |  | 36 | 88 | 94 | 130 | 62 | 868 | 458 | 234 | 224 | 125 | 286
|  |  |  | Group |  | 26 | 31 | [9 empty] | 57 | 57 | 57
B. Khavda Wind (Additional for Internal - 421 MW)
|  |  |  | Plan | [9 empty] | 99 |  |  | 99 |  |  |  |  | 99
PSS-11(32.2 MW)
11bAGEL MerchantAGE25CL | Merchant |  | 98.8 | Rephase | [9 empty] | 99 |  |  | 99 |  |  |  |  | 99
PSS-14(67.6 MW)
|  |  |  | Actual / Fcst | [9 empty] | 31 |  | 68 | 99 |  |  |  |  | 99
|  |  |  | Plan | [9 empty] | 42 | 156 | 114 | 312 |  |  |  |  | 312
12bAGEL MerchantAGE26AL | Merchant | PSS-12 | 312 | Rephase | [9 empty] | 42 | 156 | 114 | 312 |  |  |  |  | 312
|  |  |  | Actual / Fcst | [10 empty] | 156 | 156 | 312 |  |  |  |  | 312
|  |  |  | Plan | [8 empty] | 10 |  |  |  | 10 |  |  |  | 10
13AGEL MerchantAGE25BL | Merchant | PSS-09 | 10.4 | Rephase | [8 empty] | 10 |  |  |  | 10 |  |  |  | 10
|  |  |  | Actual / Fcst | [9 empty] | 10 |  |  | 10 |  |  |  |  | 10
|  |  |  | Plan | [8 empty] | 10 | 140 | 156 | 114 | 421 |  |  |  | 10 | 411
PPA
|  |  |  | Merchant | [8 empty] | 10 | 140 | 156 | 114 | 421 |  |  |  | 10 | 411
Group
|  |  |  | Rephase | [8 empty] | 10 | 140 | 156 | 114 | 421 |  |  |  | 10 | 411
PPA
B. Subtotal (Additional for Internal - 421 MW) |  |  | 421
|  |  |  | Merchant | [8 empty] | 10 | 140 | 156 | 114 | 421 |  |  |  | 10 | 411
Group
|  |  |  | Actual / Fcst | [9 empty] | 42 | 156 | 224 | 421 |  |  |  |  | 421
PPA
|  |  |  | Merchant | [9 empty] | 42 | 156 | 224 | 421 |  |  |  |  | 421
Group
C. Mundra Wind - 76 MW (Chairman)
|  |  |  | Plan | [11 empty] | 76 | 76 |  |  |  |  | 76
1Merchant-WindAWEK3L | Merchant | Mundra North | 198 | Rephase | [11 empty] | 76 | 76 |  |  |  |  | 76
|  |  |  | Actual / Fcst | [11 empty] | 76 | 76 |  |  |  |  | 76
|  |  |  | Plan | [11 empty] | 76 | 76 |  |  |  |  | 76
PPA
|  |  |  | Merchant | [11 empty] | 76 | 76 |  |  |  |  | 76
Group
|  |  |  | Rephase | [11 empty] | 76 | 76 |  |  |  |  | 76
PPA
C. Mundra Wind |  |  | 198
|  |  |  | Merchant | [11 empty] | 76 | 76 |  |  |  |  | 76
Group
|  |  |  | Actual / Fcst | [11 empty] | 76 | 76 |  |  |  |  | 76
PPA
|  |  |  | Merchant | [11 empty] | 76 | 76 |  |  |  |  | 76
Group
D. Mundra Wind - (Additional for Internal 224.4)
|  |  |  | Plan | [9 empty] | 116 | 116 | 17 | 248 |  |  |  |  | 248
1Merchant-WindAWEK3L | Merchant | Mundra North | 198 | Rephase | [9 empty] | 66 | 56 |  | 122 |  |  |  |  | 122
|  |  |  | Actual / Fcst | [11 empty] | 83 | 83 |  |  |  |  | 83