## KH Solar Actual
Phase-III: Khavda Solar Projects Monthly COD Actuals & Forecast (MWac) | [15 empty] | TR Done in Nov-25 but COD in Dec-25 | [7 empty] | 2025-12-30 |  |  | In addition to COD |  |  | Physical Progress Status till 27/28-Dec |  |  |  | Manpower as per DPR
Priority | Project | SPV | Plot No | Category | Category | MMS Type | Module Source | Capacity (MWac) | OL | Capacity (MWdc) | PSS No. | PSS Charging Date | SCOD | 2025-04-01 | 2025-05-01 | 2025-06-01 | 2025-07-01 | 2025-08-01 | 2025-09-01 | 2025-10-01 | 2025-11-01 | 2025-12-01 | 2026-01-01 | 2026-02-01 | 2026-03-01 |  | Charging | Trail Run | Trail Run Certificate | Piling | MMS (Purlin) | Module | IDT | Avaliable as of 27/28-Dec | Required
A. Khavda Solar Projects
1 | AGEL Merchant | ARE56L | S-08 | Merchant | Merchant | HSAT | ALMM | 250 | 1.37 | 342.5 | PSS-09 | 2024-11-16 |  | 2025-05-01: 75; 2025-06-01: 50; 2025-08-01: 125; 2025-09-01: 0 |  | 0 | 0 | 0 | Completed | Completed | Completed | Completed
2 | AGEL Merchant | ARE56L | A-02 | Merchant | Merchant | HSAT | ALMM | 50 | 1.37 | 68.5 | PSS-04 | 2025-02-26 |  | 2025-05-01: 50; 2025-06-01: 0; 2025-07-01: 0; 2025-08-01: 0; 2025-09-01: 0 |  | 0 | 0 | 0 | Completed | Completed | Completed | Completed
3 | MLP AP New | ARE57L | A-11 | PPA | PPA | HSAT | China | 187.5 | 1.36 | 255 | PSS-13 | 2025-02-20 | 15-Jun-29 (LTA +15D) | 2025-04-01: 75; 2025-05-01: 112.5; 2025-06-01: 0; 2025-07-01: 0; 2025-08-01: 0; 2025-09-01: 0 |  | 0 | 0 | 0 | Completed | Completed | Completed | Completed
4 | MLP AP New | ARE57L | A-12 | PPA | PPA | HSAT | China | 350 | 1.35 | 472.5 | PSS-13 | 2025-02-20 | 15-Jun-29 (LTA +15D) | 2025-05-01: 50; 2025-06-01: 175; 2025-11-01: 125 |  |  |  |  | Completed | Completed | Completed | Completed | 0 | 0
5 | SECI H-3 | AHEJ5L | A-13 | PPA | PPA | FT | China |  | 1.4 | 0 | PSS-05 | 2025-03-05 | 31-Dec-25 (LTA) | 2025-04-01: 145; 2025-06-01: 150; 2025-08-01: 50; 2025-09-01: 75; 2025-10-01: 75; 2025-12-01: 75 |  |  |  |  | Completed | Completed | Completed | Completed | 7 | 7
6 | AGEL Merchant | ARE45L | A-14 | Merchant | Merchant | HSAT | ALMM | 250 | 1.37 | 342.5 | PSS-05 | 2025-03-05 |  | 2025-04-01: 50; 2025-06-01: 125; 2025-09-01: 75; 2025-10-01: 0 |  |  |  |  | Completed | Completed | Completed | Completed
7 | MLP T3 AP | ARE56L | S-06 | PPA | PPA | HSAT | China | 500 | 1.37 | 685 | PSS-10 | 2025-03-25 | 2025-11-29 | 2025-04-01: 100; 2025-06-01: 137.5; 2025-08-01: 87.5; 2025-09-01: 100; 2025-11-01: 75 |  |  |  |  | Completed | Completed | Completed | Completed | 0 | 0
P-01 | Google Hybrid | ARE3L | A-6 | Merchant-Google | Merchant | HSAT | ALMM | 25 | 1.35 | 33.75 | PSS-08 | 2025-07-13 | - | 2025-07-01: 25; 2025-08-01: 0; 2025-09-01: 0; 2025-10-01: 0; 2025-12-01: 0 |  |  |  |  | Completed | Completed | Completed | Completed
P-02 | AGEL Merchant | ASEJ6PL | A-6 | Merchant-Hybrid | Merchant | HSAT | ALMM | 35 | 1.35 | 47.25 | PSS-08 | 2025-07-13 | - | 2025-07-01: 35; 2025-08-01: 0; 2025-09-01: 0; 2025-10-01: 0; 2025-12-01: 0 |  |  |  |  | Completed | Completed | Completed | Completed
P-03 | AGEL Hybrid Merchant | AGE25BL | S-8 | Merchant-Hybrid | Merchant | HSAT | ALMM | 100 | 1.35 | 135 | PSS-09 | 2024-11-16 | - | 2025-09-01: 100 |  |  |  |  | Completed | Completed | Completed | Completed
P-04 | AGEL Merchant | AHEJ5L | A-15a | Merchant | Merchant | HSAT | ALMM | 150 | 1.35 | 202.5 | PSS-08 | 2025-07-13 | - | 2025-09-01: 50; 2026-01-01: 50; 2026-02-01: 50 |  |  |  |  | 97% | 81.7% | 62% | C:92%; E:83% | 360 | 240
P-05 | AGEL Hybrid Merchant | AGE26BL | S-5 | Merchant-Hybrid | Merchant | HSAT | ALMM | 292 | 1.35 | 394.2 | PSS-10 | 2025-08-07 | - | 0 | 0 | 0 | 0 | 0 | 50 | 0 | 50 | 50 | 75 | 67 | 0 | 0 |  |  | 0 | 99.4% | 89.6% | 58.4% | C:100%; E:83% | 358 | 480
P-05a | AGEL Hybrid Merchant | AGE26BL | S-5 | Merchant-Hybrid | Merchant | HSAT | ALMM | 142 | 1.35 | 191.7 |  | 2025-08-07 | - | 2025-09-01: 50; 2025-11-01: 50; 2026-02-01: 42
P-05b | AGEL Merchant | AGE26BL | S-5 | Merchant-Hybrid | Merchant | HSAT | ALMM | 150 | 1.35 | 202.5 |  | 2025-08-07 | - | 2025-12-01: 50; 2026-01-01: 75; 2026-02-01: 25
P-06 | AGEL Merchant | AGE24L | S-5 | Merchant | Merchant | HSAT | ALMM | 150 | 1.35 | 202.5 | PSS-10 | 2025-08-07 | - | 2026-01-01: 62.5; 2026-02-01: 87.5 |  |  |  |  | 98% | 81.7% | 46.43% | C:100%; E:83% | 520 | 380
P-07 | AGEL Merchant | AGE24L | A-14 | Merchant | Merchant | HSAT | ALMM | 150 | 1.35 | 202.5 | PSS-05 | 2025-03-05 | - | 2026-01-01: 75; 2026-02-01: 75 |  |  |  |  | 95% | 48.7% | 13.3% | C:50%; E:50% | 412 | 840
P-08 | Cement - Hybrid | ACL | A-1 | Cement - Hybrid | Group | FT | ALMM | 125 | 1.36 | 170 | PSS-04 | 2025-02-26 | - | 2025-09-01: 50; 2025-12-01: 75 |  |  |  |  | Completed | Completed | Completed | Completed
P-09 | MLP T3 AP | AGE25CL | A-6 | PPA | PPA | HSAT | China | 75 | 1.35 | 101.25 | PSS-08 | 2025-07-13 | 2025-11-29 | 2025-12-01: 75; 2026-03-01: 0 |  |  |  |  | Completed | Completed | Completed | Completed
P-10 | MLP T1 J&K | AGE26AL | A-16a | PPA | PPA | FT | SEA | 50 | 1.3306 | 66.53 | PSS-06 | 2025-12-06 | 2026-01-12 | 2026-01-01: 50 |  |  |  |  | Completed | Completed | Completed | Completed | 129 | 250
P-11 | MLP T1 CG | AGE26AL | A-16b | PPA | PPA | FT | SEA | 200 | 1.3181 | 263.62 | PSS-06 | 2025-12-06 | 2026-01-12 | 2026-01-01: 175; 2026-02-01: 25 |  |  |  |  | 77% | 41.7% | 27.8% | C:63%; E:63% | 659 | 1050
P-12 | MLP T1 TN | AGE26AL | A-16c | PPA | PPA | FT | SEA | 167 | 1.3293 | 222 | PSS-06 | 2025-12-06 | 2026-01-12 | 2026-01-01: 100; 2026-02-01: 67 |  |  |  |  | 60.93% | 1.926% |  | C:0%; E:0% | 331 | 1020
P-13 | MLP T1 OR | AGE26AL | A-16d | PPA | PPA | FT | SEA | 333 | 1.3243 | 441 | PSS-06 | 2026-01-27 | 2026-01-12 | 2026-01-01: 150; 2026-02-01: 183 |  | 0 | 0 | 0 | 52.39% | 3% |  | C:15%; E:11% | 304 | 1620
P-14 | MLP T1 TR | AGE26AL | A10a | PPA | PPA | FT | SEA | 50 | 1.36 | 68 | PSS-03 | 2024-03-22 | 08-Dec-25 (LTA -23D) | 2025-10-01: 50 |  | 0 | 0 |  | 99.52% | 96.2% | 91% | Completed | 56 | 90
P-15 | MLP T3 AP | AGE25CL | A-6 | PPA | PPA | FT | China | 425 | 1.36 | 578 | PSS-08 | 2025-10-31 | 2025-11-29 | 2026-01-01: 100; 2026-02-01: 150; 2026-03-01: 175 |  | 0 | 0 | 0 | 67.8% | 18.13% |  | C:59%; E:47% | 794 | 1420
| Subtotal (A) | [6 empty] | 3914.5 |  | 5294.1 |  |  |  | 370 | 287.5 | 637.5 | 60 | 262.5 | 500 | 125 | 250 | 275 | 837.5 | 704.5 | 175 |  | 0 | 0 | 0 |  |  |  |  | 3930 | 7397
D1. Khavda Solar (Copper + Merchant - 50 MW)
P-18a | KCTL | KCTL | A-15a | Group | Group | HSAT | ALMM | 12.5 | 1.35 | 16.875 | PSS-08 | 2025-10-31 | - | 2026-02-01: 12.5 |  | 0 | 0 | 0 | [5 empty] | 30
P-18b | MCIPL | MCIPL | A-15a | Group | Group | HSAT | ALMM | 12.5 | 1.35 | 16.875 | PSS-08 | 2025-10-31 | - | 2026-02-01: 12.5 |  | 0 | 0 | 0 | [5 empty] | 30
P-19 | AGEL Merchant | ASEJo6PL | A-15a | Merchant | Merchant | HSAT | ALMM | 25 | 1.35 | 33.75 | PSS-08 | 2025-10-31 | - | 2026-02-01: 25 |  | 0 | 0 | 0 | [5 empty] | 60
| Subtotal (D1) | [6 empty] | 50 |  | 67.5 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50 | 0 |  | 0 | 0 | 0 | [5 empty] | 120
D2. Khavda Solar (Additional from Internal - 650 MW)
P-16 | AGEL Hybrid Merchant | AHEJ5L | S-4 | Merchant | Merchant | HSAT | ALMM | 300 | 1.35 | 405 | PSS-11 | 2025-12-05 | - | [13 empty] | 0 | 0 | 0 | [5 empty] | 890
P-17 | MLP AP New | ARE57L | A-12 | PPA | PPA | HSAT | China | 350 | 1.35 | 472.5 | PSS-13 | 2025-02-20 | 15-Jun-29 (LTA +15D) | [13 empty] | 0 | 0 | 0 | 98.61% | 1.87% | 0% | C:60%; E:7% |  | 870
| Subtotal (D2) | [6 empty] | 650 |  | 877.5 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  |  |  | 0 | 1760
Overall Total (A + D1 + D2) | [7 empty] | 4614.5 |  | 6239.1 |  |  |  | 370 | 287.5 | 637.5 | 60 | 262.5 | 500 | 125 | 250 | 275 | 837.5 | 754.5 | 175 |  | 0 | 0 | 0 |  |  |  |  | 3930 | 9277
[11 empty] | PSS-03 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 50 | 0 | 0 | 0 | 0 | 0
[11 empty] | PSS-04 |  |  | 0 | 50 | 0 | 0 | 0 | 50 | 0 | 0 | 75 | 0 | 0 | 0
[11 empty] | PSS-05 |  |  | 195 | 0 | 275 | 0 | 50 | 150 | 75 | 0 | 75 | 75 | 75 | 0
[11 empty] | PSS-06 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 475 | 275 | 0
[11 empty] | PSS-08 |  |  | 0 | 0 | 0 | 60 | 0 | 50 | 0 | 0 | 75 | 150 | 250 | 175
[11 empty] | PSS-09 |  |  | 0 | 75 | 50 | 0 | 125 | 100 | 0 | 0 | 0 | 0 | 0 | 0
[11 empty] | PSS-10 |  |  | 100 | 0 | 137.5 | 0 | 87.5 | 150 | 0 | 125 | 50 | 137.5 | 154.5 | 0
[11 empty] | PSS-11 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[11 empty] | PSS-13 |  |  | 75 | 162.5 | 175 | 0 | 0 | 0 | 0 | 125 | 0 | 0 | 0 | 0
2642.5